FaceMetrics

Series A Investment Proposal

MVP to Global Production — Development Plan & Capital Requirements

The measurement layer for online eyewear

| Document | Series A Business Proposal |
| --- | --- |
| Round | Series A |
| Raise Target | $8.5M |
| Use of Funds — Product & Eng | $3,452,565 (12-month build) |
| Scope | Global web + API · Top-3 EHR integration · B2B + B2C |
| Infrastructure | Amazon Web Services (multi-region) |
| Date | June 2026 |
| Classification | Confidential — For Investor Review |

# 1. Executive Summary

FaceMetrics is raising a $8.5M Series A to move its validated MVP to global production. The platform uses computer vision to capture optician-grade facial measurements — pupillary distance, bridge width, lens height, face width, and temple length — from any device camera, using a credit card, ruler, or passport as a calibration reference. It serves both B2C consumers and B2B partners through a documented API and white-label widget.

This proposal details the engineering plan and capital required to deliver a worldwide, production-grade platform over 12 months: a globally available web application, a full API with SDKs, integration with the three leading optical EHR systems, and the security and compliance foundation (SOC 2 Type II, HIPAA, GDPR, BIPA) required to operate in the clinical market. All infrastructure is built on Amazon Web Services across US, EU, and APAC regions.

HEADLINE: Total product and engineering investment to reach global production: $3,452,565 over 12 months, comprising 17,520 engineering hours, $430,000 in one-time compliance and legal costs, $171,960 in first-year AWS infrastructure, and a 15% contingency.

The $8.5M raise covers this $3,452,565 build plus go-to-market, initial team scaling, and 18 months of operating runway to reach the revenue inflection point where the API session volume and analytics tiers become self-sustaining.

# 2. The Opportunity

Online eyewear is a large, fast-growing, and structurally underserved market. The core barrier to online prescription eyewear — the inability to capture accurate facial measurements remotely — is precisely what FaceMetrics solves.

| Market Metric | Figure | Relevance |
| --- | --- | --- |
| Global eyewear market (TAM) | $147B | Total addressable category |
| Online & DTC eyewear (SAM) | $38B | Directly served segment |
| API + widget platform revenue (SOM, 5yr) | $2.4B | FaceMetrics obtainable share |
| Online eyewear return rate | 30–40% | Primary pain FaceMetrics reduces |
| People needing corrective lenses worldwide | 1B+ | Global B2C reach potential |
| Annual online eyewear growth rate | ~27% | Category tailwind |

The measurement problem has no dominant neutral solution. Existing tools are single-purpose (PD only), poorly documented, or locked inside vertically integrated retailers. A neutral, accurate, API-first measurement layer is the natural infrastructure outcome — and first-mover advantage compounds through integration switching costs and a proprietary outcome-data flywheel.

# 3. Scope: MVP to Global Production

The current MVP validates the core measurement approach. This investment funds the transition to a production platform available worldwide, across eight coordinated workstreams.

| Workstream | Delivers |
| --- | --- |
| Core CV & Measurement Engine | Multi-angle capture, asymmetry detection, confidence scoring, low-end device optimization, clinical accuracy validation |
| Web Application (B2C + B2B) | Production web app, offline PWA, white-label widget SDK, consumer face-profile accounts, 10-language localization, assessment builder |
| API Platform & SDKs | Production REST API, OAuth/SMART on FHIR auth, webhooks, JS/iOS/Android SDKs, developer portal and sandbox |
| EHR Integrations (Top 3) | FHIR R4 server, RevolutionEHR, Eyefinity, and Epic integrations, HL7 v2 middleware, terminology mapping |
| AWS Infrastructure & DevOps | Multi-region architecture (US/EU/APAC), CI/CD, auto-scaling, observability, disaster recovery, data residency |
| Security & Compliance | SOC 2 Type II, HIPAA safeguards, BIPA/GDPR consent, penetration testing, encryption and key management |
| QA, Testing & Launch | Automated test suites, cross-device QA, accuracy regression, load testing, technical documentation |
| Program Management | Product management and technical program coordination across all workstreams |

# 4. Development Hours & Cost Breakdown

The following breakdown details every workstream, the roles involved, hours, and fully-loaded cost. Rates reflect blended senior health-technology engineering rates inclusive of overhead. Total engineering effort is 17,520 hours across a 12-month delivery window.

### 4.1 Blended Loaded Rates

| Role | Rate (USD/hr) | Role | Rate (USD/hr) |
| --- | --- | --- | --- |
| Principal Engineer | $165 | Security Engineer | $175 |
| ML/CV Engineer | $155 | Compliance Lead | $195 |
| Senior Engineer | $140 | DevOps Engineer | $145 |
| Mid Engineer | $105 | Product/Program Mgr | $130 |
| Product Designer | $115 | QA Engineer | $95 |
| Technical Writer | $85 |  |  |

### 4.2 Detailed Workstream Breakdown

Core CV & Measurement Engine  — 2,080 hrs · $322,400

| Task | Role | Hours | Cost |
| --- | --- | --- | --- |
| Multi-angle capture pipeline (temple length 3D) | ML/CV Engineer | 480 | $74,400 |
| Asymmetry detection engine + calibration | ML/CV Engineer | 360 | $55,800 |
| Confidence scoring & IQR outlier system | ML/CV Engineer | 240 | $37,200 |
| Passport + ruler + card calibration hardening | ML/CV Engineer | 320 | $49,600 |
| Model optimization for low-end devices (WASM/WebGL) | ML/CV Engineer | 400 | $62,000 |
| Accuracy validation harness + clinical benchmarking | ML/CV Engineer | 280 | $43,400 |

Web Application (B2C + B2B)  — 3,100 hrs · $390,200

| Task | Role | Hours | Cost |
| --- | --- | --- | --- |
| Production React web app rebuild | Senior Engineer | 520 | $72,800 |
| Progressive Web App + offline mode | Senior Engineer | 360 | $50,400 |
| White-label widget SDK | Senior Engineer | 440 | $61,600 |
| Consumer face-profile account system | Mid Engineer | 480 | $50,400 |
| Multilingual/i18n (10 languages) + a11y WCAG 2.1 AA | Mid Engineer | 400 | $42,000 |
| Assessment builder (no-code) | Senior Engineer | 380 | $53,200 |
| Frontend design system + UX | Product Designer | 520 | $59,800 |

API Platform & SDKs  — 2,380 hrs · $319,900

| Task | Role | Hours | Cost |
| --- | --- | --- | --- |
| REST API v1 productionization + OpenAPI | Principal Engineer | 420 | $69,300 |
| OAuth 2.0 + SMART on FHIR authorization | Senior Engineer | 360 | $50,400 |
| Webhook system + event streaming | Senior Engineer | 280 | $39,200 |
| JS/TS, React, iOS, Android SDKs | Senior Engineer | 640 | $89,600 |
| Rate limiting, quota, billing metering | Mid Engineer | 320 | $33,600 |
| Developer portal + sandbox | Mid Engineer | 360 | $37,800 |

EHR Integrations (Top 3)  — 2,400 hrs · $353,600

| Task | Role | Hours | Cost |
| --- | --- | --- | --- |
| FHIR R4 server (HAPI) + USCDI v3 mapping | Principal Engineer | 480 | $79,200 |
| RevolutionEHR integration | Senior Engineer | 360 | $50,400 |
| Eyefinity integration + partner cert | Senior Engineer | 420 | $58,800 |
| Epic integration + Connector Builder cert | Principal Engineer | 560 | $92,400 |
| HL7 v2 translation middleware | Senior Engineer | 340 | $47,600 |
| LOINC/SNOMED terminology mapping | Mid Engineer | 240 | $25,200 |

AWS Infrastructure & DevOps  — 1,880 hrs · $272,600

| Task | Role | Hours | Cost |
| --- | --- | --- | --- |
| Multi-region architecture (US/EU/APAC) | DevOps Engineer | 480 | $69,600 |
| CI/CD pipelines + IaC (Terraform) | DevOps Engineer | 360 | $52,200 |
| Auto-scaling, load balancing, CDN (CloudFront) | DevOps Engineer | 320 | $46,400 |
| Observability (CloudWatch, X-Ray, alerting) | DevOps Engineer | 280 | $40,600 |
| Disaster recovery + backup + failover | DevOps Engineer | 240 | $34,800 |
| Data residency segregation (EU/US) | DevOps Engineer | 200 | $29,000 |

Security & Compliance  — 1,960 hrs · $355,400

| Task | Role | Hours | Cost |
| --- | --- | --- | --- |
| SOC 2 Type II readiness + controls | Security Engineer | 480 | $84,000 |
| HIPAA technical safeguards implementation | Security Engineer | 360 | $63,000 |
| BIPA/GDPR consent architecture | Compliance Lead | 320 | $62,400 |
| Penetration testing + remediation | Security Engineer | 280 | $49,000 |
| Encryption (TLS 1.3, at-rest), key management | Security Engineer | 220 | $38,500 |
| Compliance documentation + audit prep | Compliance Lead | 300 | $58,500 |

QA, Testing & Launch  — 2,040 hrs · $190,200

| Task | Role | Hours | Cost |
| --- | --- | --- | --- |
| Automated test suite (unit/integration/e2e) | QA Engineer | 560 | $53,200 |
| Cross-device/browser QA matrix | QA Engineer | 400 | $38,000 |
| Accuracy regression testing | QA Engineer | 280 | $26,600 |
| Load & performance testing | QA Engineer | 240 | $22,800 |
| Security & compliance QA | QA Engineer | 200 | $19,000 |
| Technical documentation | Technical Writer | 360 | $30,600 |

Program Management  — 1,680 hrs · $218,400

| Task | Role | Hours | Cost |
| --- | --- | --- | --- |
| Product management (12 months) | Product/Program Mgr | 1,200 | $156,000 |
| Technical program coordination | Product/Program Mgr | 480 | $62,400 |

### 4.3 Labor Cost Summary

| Workstream | Hours | Cost |
| --- | --- | --- |
| Core CV & Measurement Engine | 2,080 | $322,400 |
| Web Application (B2C + B2B) | 3,100 | $390,200 |
| API Platform & SDKs | 2,380 | $319,900 |
| EHR Integrations (Top 3) | 2,400 | $353,600 |
| AWS Infrastructure & DevOps | 1,880 | $272,600 |
| Security & Compliance | 1,960 | $355,400 |
| QA, Testing & Launch | 2,040 | $190,200 |
| Program Management | 1,680 | $218,400 |
| TOTAL LABOR | 17,520 | $2,422,700 |

# 5. AWS Infrastructure Costs

FaceMetrics runs entirely on Amazon Web Services with a multi-region architecture spanning US, EU (Frankfurt), and APAC regions to meet data residency requirements and deliver low-latency worldwide access. The figures below reflect steady-state production scale; early-stage costs will be lower and scale with session volume.

| AWS Service | Monthly | Annual |
| --- | --- | --- |
| Compute (ECS/Fargate, Lambda) | $4,200/mo | $50,400/yr |
| FHIR data store + RDS (multi-AZ) | $2,800/mo | $33,600/yr |
| CloudFront CDN + data transfer | $1,900/mo | $22,800/yr |
| S3 storage + backup | $650/mo | $7,800/yr |
| ML inference (fallback, SageMaker) | $1,400/mo | $16,800/yr |
| Cognito / auth infra | $480/mo | $5,760/yr |
| Monitoring (CloudWatch, X-Ray) | $520/mo | $6,240/yr |
| WAF + security services | $780/mo | $9,360/yr |
| Multi-region replication | $1,600/mo | $19,200/yr |
| TOTAL AWS | $14,330/mo | $171,960/yr |

Architecture note: FaceMetrics performs computer-vision processing client-side in the browser, so server-side compute scales with API calls and FHIR data operations rather than video processing — keeping infrastructure costs materially lower than a server-side vision pipeline would require. AWS activate credits (up to $100K for eligible startups) can offset a significant portion of year-one infrastructure cost.

# 6. One-Time Compliance & Legal Costs

Operating in the clinical and biometric-data space requires substantial one-time investments in compliance, legal, and clinical validation. These are non-negotiable prerequisites for EHR integration and international operation — and each also functions as a competitive moat that later entrants must replicate.

| Item | Cost |
| --- | --- |
| SOC 2 Type II audit (external firm) | $65,000 |
| Penetration testing (external) | $35,000 |
| Legal - HIPAA/BIPA/GDPR counsel | $85,000 |
| Legal - EHR partner agreements + IP | $60,000 |
| Clinical validation study (500 patients) | $120,000 |
| LOINC code assignment + terminology consult | $25,000 |
| FDA regulatory counsel (SaMD boundary) | $40,000 |
| TOTAL ONE-TIME COSTS | $430,000 |

STRATEGIC: These compliance investments are a moat, not just a cost. Once FaceMetrics holds SOC 2 Type II, HIPAA attestation, and peer-reviewed clinical validation, competitors cannot enter clinical accounts without replicating 12–18 months of the same work.

# 7. Total Project Cost — MVP to Production

| Category | Amount | % of Build |
| --- | --- | --- |
| Engineering labor (17,520 hrs) | $2,422,700 | 70% |
| One-time compliance & legal | $430,000 | 12% |
| AWS infrastructure (year 1) | $171,960 | 5% |
| Contingency (15%) | $427,905 | 12% |
| TOTAL PROJECT COST | $3,452,565 | 100% |

# 8. 12-Month Delivery Timeline

| Quarter | Milestones | Cumulative Spend |
| --- | --- | --- |
| Q1 (Mo 1–3) | CV engine hardening, FHIR server, AWS foundation, SOC 2 kickoff, RevolutionEHR integration begins | ~25% |
| Q2 (Mo 4–6) | Production web app + PWA, API v1 + SDKs, RevolutionEHR live, clinical validation study runs | ~50% |
| Q3 (Mo 7–9) | Widget SDK, Eyefinity integration + partner cert, multilingual, penetration testing, BIPA/GDPR consent | ~75% |
| Q4 (Mo 10–12) | Epic Connector Builder cert, SOC 2 Type II achieved, global multi-region launch, GA release | 100% |

EHR integrations are deliberately sequenced by complexity: RevolutionEHR (open developer program, fastest) in Q1–Q2, Eyefinity (partner-approval gated) in Q3, and Epic (Connector Builder certification, longest cycle) in Q4. This ensures at least one production EHR integration is live by mid-year, de-risking the clinical go-to-market.

# 9. Use of Funds — $8.5M Series A

The $3,452,565 development build sits within a broader $8.5M raise that funds the company through the revenue inflection point. Allocation:

| Category | Allocation | Amount | Purpose |
| --- | --- | --- | --- |
| Product & Engineering | 41% | $3,452,565 | MVP to global production (this proposal) |
| Go-to-Market & Sales | 22% | $1,870,000 | DevRel, partnerships, brand deals, EHR channel |
| Team Scaling & G&A | 18% | $1,530,000 | Key hires, finance, operations, legal |
| Working Capital & Runway | 14% | $1,190,000 | 18-month operating buffer to revenue inflection |
| Reserve | 5% | $457,435 | Strategic opportunity / additional contingency |
| TOTAL RAISE | 100% | $8,500,000 |  |

# 10. Investment Rationale & Milestones

This Series A takes FaceMetrics from a validated MVP to a defensible, revenue-generating global platform. The capital funds four value-creating milestones that de-risk the business and set up a strong Series B or strategic exit:

- Production platform live worldwide — web, API, and SDKs available across US, EU, and APAC by month 12.

- Three EHR integrations in production — RevolutionEHR, Eyefinity, and Epic, covering the majority of the US optometry and hospital ophthalmology market.

- Full compliance moat established — SOC 2 Type II, HIPAA, GDPR, BIPA, and peer-reviewed clinical validation, unlocking the clinical and telehealth markets competitors cannot easily enter.

- Revenue inflection reached — API session volume plus analytics tiers cross the threshold to self-sustaining growth, positioning for a Series B at a materially higher valuation.

THE MOAT: The compliance and data-flywheel investments funded here are the durable moat: by the time a competitor is organized, FaceMetrics holds the integrations, the certifications, and a proprietary dataset of measurement outcomes that cannot be replicated quickly.

Disclaimer

This document contains forward-looking projections and estimates prepared for investor evaluation. Development hours, costs, and timelines are good-faith estimates based on current scope and prevailing market rates, and are subject to change as scope and market conditions evolve. It does not constitute an offer to sell securities.

—  End of Proposal  —