## Sprint 1 Backlog
Rekab-Compute MVP · Sprint 1 Backlog · 2026-07-07 → 2026-07-18
Sprint Goal: Monorepo scaffolded, CI/CD live, OSS cloud infrastructure provisioned, local dev running, shared TypeScript types published, TLS enforced.
Epic # | Story # | Story Title | User Story | Acceptance Criteria | Story Points | T-Shirt Size | Priority | Owner (Role) | Dependencies | Status | Notes
E1 | E1-S1 | Set up monorepo structure | As a developer, I want a monorepo (packages: sdk-core, widget, backend, ml-fallback) so all packages share types, tooling, and versioning. | • Repo initialised with pnpm workspaces (or Nx) • Four packages exist: sdk-core, widget, backend, ml-fallback • Root-level lint + test scripts run across all packages • README documents package responsibilities | 3 | S | Must Have | Tech Lead | None | To Do | Use pnpm workspaces + Turborepo (replaces Nx). Turborepo is open-source (Vercel), zero cost, simpler config for a 4-package monorepo. Free remote caching via GitHub Actions cache — no Nx Cloud subscription needed.
E1 | E1-S2 | Configure CI/CD pipeline | As a developer, I want GitHub Actions to lint, test, build, and deploy on every PR so broken code never reaches main. | • PR triggers: lint, type-check, unit tests for all packages • Main merge triggers: build + deploy to staging • Badge in README shows pipeline status • Secrets stored in GitHub Secrets (not hardcoded) | 3 | S | Must Have | DevOps / Tech Lead | E1-S1 | To Do | Staging deploy can be a no-op placeholder until infra is live
E1 | E1-S3 | Provision cloud infrastructure (IaC) — OSS stack | As an engineer, I want all cloud resources provisioned via Terraform so environments are reproducible and diff-able. | • Config created for: API Gateway, Fly.io (compute), Neon (Postgres 15, serverless), Cloudflare R2 + CDN, Upstash Redis, Doppler (secrets) • Dev + staging environments provisioned (Fly.io apps, Neon dev branch, Doppler configs) • `fly deploy --dry-run` runs clean; Neon dev branch connected and accessible • Infrastructure diagram updated in repo docs • Migration decision log documents OSS → AWS RDS/ECS path at Series A | 8 | L | Must Have | DevOps Engineer | E1-S1, E1-S2 | To Do | Neon replaces Aurora Serverless v2: true scale-to-zero (Aurora min ~$43/mo idle), PostgreSQL-compatible (no schema/migration changes), ~⅙ cost pre-revenue. Plan: migrate to AWS RDS + ECS Fargate at Series A (~Month 18-20) for enterprise SLAs.
E1 | E1-S4 | Configure local dev environment | As a developer, I want a single `docker compose up` to start the full local stack so onboarding takes < 30 minutes. | • docker-compose.yml spins up: FastAPI backend, PostgreSQL 15, Redis • `.env.example` documents all required variables • `make dev` (or npm script) starts all services • New-engineer setup guide in CONTRIBUTING.md | 2 | XS | Must Have | Tech Lead | E1-S1 | To Do | Postgres 15 + Redis 7 in Docker Compose must match Neon and Upstash versions to avoid env parity surprises. Check Neon Postgres version at project creation.
E1 | E1-S5 | Publish shared TypeScript types (sdk-core) | As a developer, I want shared TypeScript types for MeasurementResult, AsymmetryFlag, CalibrationMode, and SessionToken so the widget and API client never diverge. | • sdk-core package exports all core types with JSDoc • Types: MeasurementResult, MonocularPD, AsymmetryFlag, AsymmetrySeverity, CalibrationMode, SessionToken, ConfidenceScore • Unit tests cover type guards / validators • Package version follows semver; published to internal npm registry or consumed via workspace path | 2 | XS | Must Have | Full-Stack Dev | E1-S1 | To Do | This is the contract between widget, API client, and backend — changes here are breaking changes
E1 | E1-S6 | Secrets & environment config management | As an engineer, I want centralised secrets management so credentials are never committed to source code. | • All secrets stored in Doppler free tier (prod/staging/dev configs) and .env files (local, git-ignored) • Application reads secrets via environment variables at runtime • `detect-secrets` pre-commit hook blocks accidental credential commits • Rotation runbook documented • Doppler free tier (≤5 configs) sufficient pre-revenue; upgrade to Team ($10/mo) pre-SOC 2 | 2 | XS | Must Have | DevOps Engineer | E1-S3 | To Do | Doppler replaces AWS Secrets Manager (~$8/mo for 20 secrets). Doppler free tier: unlimited secrets, up to 5 configs. Add detect-secrets to pre-commit hooks in CI.
E2 | E2-S1 | Database schema & migrations framework | As a developer, I want a versioned migration framework (Alembic) and initial schema so the database evolves safely. | • Alembic configured and connected to Neon (Postgres 15) • Initial migration: tenants, api_keys, sessions, measurements tables • Migrations run automatically on deploy • Rollback tested on local Postgres (matches Neon version) | 3 | S | Must Have | Backend Dev | E1-S3, E1-S4 | To Do | Schema must include tenant_id on all measurement tables from day one to avoid costly backfill later
E2 | E2-S2 | FastAPI application skeleton & health endpoint | As a developer, I want a running FastAPI app with a health endpoint so CI/CD can confirm the service is alive after deploy. | • FastAPI app boots without errors • GET /health returns {status: ok, version: x.x.x} • OpenAPI schema auto-generated at /docs • Structured JSON logging (stdout) with request IDs • CORS configured (allow-list, not wildcard) | 3 | S | Must Have | Backend Dev | E1-S3, E1-S4 | To Do | Health endpoint used by Fly.io health checks (replaces ECS Fargate target group health check)
SEC | SEC-S1 | TLS 1.3 enforcement on all endpoints | As an operator, I want all traffic to be TLS 1.3 encrypted so we meet baseline security and compliance requirements. | • Cloudflare CDN enforces HTTPS-only (redirect HTTP → HTTPS) • Custom domain uses Cloudflare auto-provisioned certificate (replaces ACM) • TLS 1.2 disabled; TLS 1.3 minimum enforced via Cloudflare SSL/TLS settings • SSL Labs scan returns A or A+ grade | 1 | XS | Must Have | DevOps Engineer | E1-S3 | To Do | Cloudflare replaces CloudFront + ACM: certificates auto-provisioned, zero egress fees (vs $0.09/GB on CloudFront), free plan covers pre-revenue traffic. No ACM us-east-1 requirement.
SEC | SEC-S2 | Branch protection & code security baseline | As a tech lead, I want branch protection rules and security scanning so main is always in a releasable state. | • Main branch requires: 1 approving review, passing CI, no force-push • GitHub Dependabot enabled for all packages • Trivy container scan in CI pipeline (open-source, no API limits; Snyk not required) • CODEOWNERS file defines review requirements per package | 1 | XS | Must Have | Tech Lead | E1-S2 | To Do | Non-negotiable before any external contractor access

## Sprint Summary
Rekab-Compute MVP – Sprint 1 Summary
Metric | Value
Sprint Number | Sprint 1
Sprint Start | 2026-07-07 (Monday)
Sprint End | 2026-07-18 (Friday)
Duration | 2 weeks / 10 working days
Total Stories | 10
Total Story Points | 28
Must Have Points | 28
Should Have Points | 0
Avg Points / Story | 2.8
Epics Covered | E1 – Project Foundation & Infrastructure E2 – Auth & Session Management (foundation) SEC – Security Baseline
Sprint Goal | Monorepo scaffolded · CI/CD live · OSS infra provisioned Local dev running · Shared TS types published · TLS enforced
Definition of Done | Code reviewed & merged · CI passing · Deployed to staging · Acceptance criteria verified
Key Risks | AWS resource limits / account setup delays (mitigate: request limit increases week –1) Terraform state backend setup (use S3 + DynamoDB locking from day 1)
Recommended Team | 1× Tech Lead · 1× DevOps Engineer · 1× Backend Dev · 1× Full-Stack Dev

## Epic Breakdown
Sprint 1 – Epic Breakdown
Epic # | Epic Name | Stories in Sprint | Story Points | % of Sprint Points | Stories
E1 | Project Foundation & Infrastructure | 6 | 19 | 67.9% | E1-S1 Monorepo structure (3pts) E1-S2 CI/CD pipeline (3pts) E1-S3 OSS cloud infrastructure IaC (8pts) E1-S4 Local dev environment (2pts) E1-S5 Shared TS types / sdk-core (2pts) E1-S6 Secrets & env config (2pts)
E2 | Auth & Session Management (foundation) | 2 | 6 | 21.4% | E2-S1 DB schema & Alembic migrations (3pts) E2-S2 FastAPI skeleton & /health endpoint (3pts)
SEC | Security & Compliance Baseline | 2 | 2 | 7.1% | SEC-S1 TLS 1.3 enforcement (1pt) SEC-S2 Branch protection & security scanning (1pt)
TOTAL | All Epics | 10 | 28 | 100%

## Sizing Guide & DoD
Rekab-Compute – Story Sizing Guide & Definition of Done
FIBONACCI STORY POINT SCALE
Points | T-Shirt | Effort / Complexity | Examples in Rekab-Compute context
1 | XS | Trivial — config change, a flag, a 1-line fix. < 2 hours. | Enable TLS flag on API Gateway · Add env variable · Update README
2 | XS | Simple, well-understood task with minimal unknowns. Half a day. | Shared TS types package with JSDoc · Docker Compose local env · Branch protection rules
3 | S | Straightforward story, clear implementation path. ~1 day. | Monorepo structure setup · CI/CD GitHub Actions workflow · FastAPI /health skeleton · DB migrations
5 | M | Moderate complexity, some design decisions required. 2–3 days. | OAuth 2.0 API key auth · Rate limiting middleware · MediaPipe Iris model integration
8 | L | Complex, cross-cutting or significant unknowns. ~1 week. Consider splitting. | AWS Terraform infra (all resources) · MediaPipe FaceMesh WASM in Web Worker · Lambda ML fallback · Asymmetry detection engine
13 | XL | Very large — should almost always be split before sprint commitment. | Full CV pipeline end-to-end · White-label widget SDK (initial build)
DEFINITION OF DONE (applies to every story)
Category | Requirement
Code | Code written, self-reviewed, and a PR opened with description linking to story #
Review | At least 1 peer code review approval; all review comments resolved
Tests | Unit tests written and passing; coverage does not decrease from baseline
CI | All CI checks pass (lint, type-check, tests, security scan)
Deploy | Merged to main and automatically deployed to staging environment
Acceptance | All acceptance criteria verified — by developer AND product owner
Docs | Any new env vars, endpoints, or architectural decisions documented (README / ADR)
No Regressions | No new errors or warnings introduced in logs or monitoring

## OSS Stack Decisions
Rekab-Compute · Sprint 1 — OSS Stack Decisions (Infrastructure ADR)
Decision log for open-source / lower-cost substitutions replacing AWS-native services in Sprint 1. Plan: migrate back to AWS-native at Series A (~Month 18–20) for enterprise SLAs + SOC 2 audit readiness.
Sprint 1 Story | Component | Replaced (AWS) | Substitute (OSS) | Monthly Saving | Key Benefit | Tradeoff / Risk | Series A Upgrade Path | Status
E1-S1 | Monorepo build tool | Nx (Cloud paid features) | Turborepo + pnpm workspaces | $0 (DX win) | Simpler config for 4-package monorepo; free remote cache via GitHub Actions | Nx has broader plugin ecosystem; Turborepo has fewer built-in generators | Keep Turborepo — no migration needed | ✅ Confirmed
E1-S3 | Database | AWS RDS Aurora Serverless v2 (~$43–80/mo idle) | Neon (serverless Postgres 15) | $24–61/mo | True scale-to-zero; PostgreSQL-compatible; Neon dev branches for PRs; ~⅙ cost | Not AWS-native; Neon SLA is 99.95% vs RDS 99.99%; less mature for high-write workloads | Migrate to AWS RDS Aurora at Series A (drop-in, no schema changes) | ✅ Confirmed
E1-S3 | Cache / Redis | AWS ElastiCache Redis (cache.t3.micro ~$12/mo) | Upstash Redis | $12–15/mo | Pay-per-request (no idle charge); 256 MB + 500K commands/mo free tier; REST + Redis API | Single-region on free tier; latency slightly higher than co-located ElastiCache | Migrate to ElastiCache at Series A for VPC co-location + SLA | ✅ Confirmed
E1-S3 | Compute / hosting | AWS ECS Fargate (~$9–15/mo small task) | Fly.io | $0–8/mo | Free tier covers 3 shared-cpu-1x machines; simpler DX (fly.toml vs task defs); fast deploys | Less AWS-native; Fly.io SLA is 99.9% vs ECS 99.99%; no VPC-native integration | Migrate to ECS Fargate at Series A for VPC, ALB, and enterprise networking | ✅ Confirmed
E1-S3 | Object storage + CDN | AWS S3 + CloudFront (~$5–10/mo incl. egress) | Cloudflare R2 + CDN | $5–10/mo | Zero egress fees; R2 free tier 10 GB + 1M ops/mo; Cloudflare CDN free | R2 lacks S3 event notifications natively; Cloudflare ecosystem vs AWS ecosystem lock-in | Optional: keep R2 long-term (zero egress is a durable advantage vs S3) | ✅ Confirmed
E1-S3 | Container registry | AWS ECR (~$0.10/GB/mo) | GitHub Container Registry (ghcr.io) | $1–3/mo | Free for public; 500 MB free for private; already integrated with GitHub Actions | Not AWS-native; requires ECR pull credentials if moving back to ECS | Migrate to ECR at Series A when deploying on ECS | ✅ Confirmed
E1-S6 | Secrets management | AWS Secrets Manager (~$0.40/secret/mo = ~$8/mo) | Doppler free tier | ~$8/mo | Free tier: unlimited secrets, up to 5 configs; better DX than Secrets Manager console; syncs to GitHub Actions + Fly.io | Doppler Team ($10/mo) required for audit logs pre-SOC 2; not AWS-native | Add Doppler Team at SOC 2 prep; consider Secrets Manager integration for RDS creds at Series A | ✅ Confirmed
SEC-S2 | Security scanning | Snyk (limited free tier, 200 scans/mo cap) | Trivy (open-source) | $0 (free vs. limited free) | Fully open-source (Apache 2.0); no API limits; scans containers, IaC, and SBOMs | Trivy has no SaaS dashboard; no PR annotations out-of-the-box (addable via trivy-action) | Keep Trivy — durable choice, no migration needed | ✅ Confirmed
ESTIMATED MONTHLY SAVING (pre-revenue, conservative → aggressive) |  |  |  | $50–97/mo ~$600–$1,164/yr